## Sheet1
TRENT RADIO "Studio C" Project: Disbursements of Trillium Funds to 28Feb03
For BoD 27Mar03 prepared 26Mar03 / jkm | YEAR 01 (ends 31Oct03) |  |  | YEAR 02 (ends 31Oct04) |  |  | YEAR 01 & 02
| Budget | To Date | Balance | Budget | To Date | Balance | Budget | To Date | Balance
01 LABOUR
a FT Digital Audio Ingest (2000hrs @ 11.50/hr /w ben) | 18500 | 0 | 18500 | 4500 | 0 | 4500 | 23000 | 0 | 23000
b Custom SQL Finding Aid Development Fees | 2000 | 0 | 2000 | 500 | 0 | 500 | 2500 | 0 | 2500
c Installation & Setup Fees | 3000 | 0 | 3000 | 1000 | 0 | 1000 | 4000 | 0 | 4000
Subtotal Labour | 23500 | 0 | 23500 | 6000 | 0 | 6000 | 29500 | 0 | 29500
0'2 EQUIPMENT & RENOVATION
a Digital Ingest & Storage
1 Digital Ingest Stations | 9329.25 | 8860.44 | 468.81 | no spending |  |  | 9329.25 | 8860.44 | 468.81
2 Data Storage Devices | 19581.1 | 14144.22 | 5436.88 |  |  |  | 19581.1 | 14144.22 | 5436.88
Subtotal Digital Ingest & Storage | 28910.35 | 23004.66 | 5905.69 |  |  |  | 28910.35 | 23004.66 | 5905.69
b Audio & Studio Equipment
1 Studio C - see attached schedule | no spending |  |  | 14920.7048 | 3043.22 | 11877.4848 | 14920.7048 | 3043.22 | 11877.4848
2 Studio B - see attached schedule |  |  |  | 4659.1484 | 1195.24 | 3463.9084 | 4659.1484 | 1195.24 | 3463.9084
Subtotal Audio & Studio Equipment |  |  |  | 19579.8532 | 4238.46 | 15341.3932 | 19579.8532 | 4238.46 | 15341.3932
Totals | 52410.35 | 23004.66 | 29405.69 | 25579.8532 | 4238.46 | 21341.3932 | 77990.2032 | 27243.12 | 50747.0832
| - | -
Total TRILLIUM Disbursement Portion | 157231.05 | 69013.98 | 226245.03

## Sheet2
Trent Radio Ledger Report 02-09-01 to 03-03-14 | [5 empty] | A | Y
1580 | 2002-10-11 | Muir, JK; 3xGlobalChairs + CR1604 | 1136 | J85 | 417.96 | 2a1 | 1
1600 | 2002-11-22 | TCIO; LynxOne AudioCard | 1167 | J131 | 469.77 | 2a1 | 1
1600 | 2002-11-22 | UPS re TCIO LynxOne AudioCard | 1167 | J132 | 38.45 | 2a1 | 1
1600 | 2002-11-22 | Art Bykov; LynxOne AudioCard | 1167 | J133 | 448.94 | 2a1 | 1
1600 | 2002-11-22 | UPS re Bykov LynxOne | 1167 | J134 | 42.78 | 2a1 | 1
1600 | 2002-11-22 | Art Bykov; 2xLynxOne AudioCard | 1167 | J135 | 906.38 | 2a1 | 1
1600 | 2002-11-22 | UPS re Bykov 2xLynxOne | 1167 | J136 | 38.45 | 2a1 | 1
1600 | 2003-01-17 | Rexall; Customs per eBay Purchase | 1181 | J235 | 9.37 | 2a1 | 1
1600 | 2003-01-17 | Premier Cda; XP2100/aBit Computer | 1181 | J242 | 2100.16 | 2a1 | 1
1600 | 2003-01-17 | Saint21380; aBit KT7 MB | 1181 | J246 | 83.3 | 2a1 | 1
1600 | 2003-01-17 | CCRA; Customs per aBit KT7 MB | 1181 | J247 | 9.37 | 2a1 | 1
1600 | 2003-01-17 | racin3wide; DAL CardD /w DB | 1181 | J248 | 76.89 | 2a1 | 1
1600 | 2003-01-17 | United Cmptrs; 2x HDisk Bus Cable | 1181 | J251 | 43.18 | 2a1 | 1
1600 | 2003-01-17 | United Cmptrs; Encore 10/100 NIC | 1181 | J252 | 21.59 | 2a1 | 1
1600 | 2003-01-17 | United Cmptrs; 3x Pentium4 2Ghz Cmptrs | 1187 | J260 | 3807 | 2a1 | 1
1600 | 2003-01-17 | United Cmptrs; 3x 15'ECable & 5PortSW | 1188 | J261 | 102.56 | 2a1 | 1
1600 | 2003-01-31 | Central Biz;; ComputerStand RipStation | 1194 | J276 | 46.17 | 2a1 | 1
1600 | 2003-01-31 | Cshway; ShelfBoards & Hrdwr RipStation | 1194 | J277 | 43.65 | 2a1 | 1
1600 | 2003-02-14 | Cshway; Hrdrw for RipStation StudioC | 1200 | J295 | 3.27 | 2a1 | 1
1600 | 2003-03-13 | Long&McQuade; Edirol SPDif/USB Interfac | 1218 | J341 | 151.2 | 2a1 | 1 | 8860.44
1600 | 2003-02-14 | Misco; APC SU1000RM2U UPS StudioC | 1200 | J290 | 944.42 | 2a2 | 1
1600 | 2003-02-14 | Hodgson,W; StudioC Wired Server Rack | 1197 | J298 | 375.65 | 2a2 | 1
1600 | 2003-03-12 | ExcelMerdian; TR_Excel_030205 DataNAS | 205737777 | J350 | 12824.15 | 2a2 | 1 | 14144.22
1600 | 2002-10-17 | Muir, JK; eBay #1386979538 GentnerAP800 | 1138 | J59 | 417.21 | 2b1 | 2
1600 | 2002-11-22 | DCom; Gentner Hybrid Coupler | 1167 | J129 | 134.84 | 2b1 | 2
1600 | 2002-11-22 | UPS re DCom Hybrid Coupler | 1167 | J130 | 31 | 2b1 | 2
1600 | 2002-11-22 | TechRecvry; Gentner Digital Hybrid | 1167 | J137 | 400.48 | 2b1 | 2
1600 | 2002-11-22 | A&ACustom re TechRecry Digital Hybrid | 1167 | J138 | 37.38 | 2b1 | 2
1600 | 2003-01-17 | A7A Broker; per Digital Hybrid | 1181 | J245 | 57.31 | 2b1 | 2
1600 | 2003-02-24 | Muir, JK; Trvl Pickup 2xDenon Turntbls | 1211 | J334 | 48 | 2b1 | 2
1600 | 2003-02-24 | Long&McQuade; 2x Denon DP-DJ151 Turntbl | 1211 | J331 | 1436.4 | 2b1 | 2
1600 | 2003-03-13 | Long&McQuade; MidiMan Delta44 | 1218 | J340 | 361.8 | 2b1 | 2
1600 | 2003-03-13 | Long&McQuade; 2x SS35C Shure Cartridge | 1218 | J342 | 118.8 | 2b1 | 2 | 3043.22
1600 | 2002-10-11 | Muir, JK; 3xGlobalChairs + CR1604 | 1136 | J85 | 969.78 | 2b2 | 2
1600 | 2002-11-22 | AAAPawnBroker; Adj CR1604 | 1167 | J126 | 72.26 | 2b2 | 2
1600 | 2002-11-22 | AirStar; Hitachi FT500MkII | 1167 | J127 | 114.98 | 2b2 | 2
1600 | 2002-11-22 | UPS; Hitachi FT5500 MkII | 1167 | J128 | 38.22 | 2b2 | 2
1620 |  | Technical Renovations |  |  | 0 |  | 2 | 1195.24
27243.12